## Readme
Airborne Observation Platform flight survey schedules by year
Last updated: July 11, 2019
The following tabs include the NEON project's annual planned flight schedules for the Airborne Observation Platform (AOP). This information is intended to provide researchers an understanding of when we intend to collect airborne data. Please note that actual date ranges for data collection may vary from the information in this document as result of weather conditions, technical issues, instrument availability and budget considerations. This document will be updated periodically so check back for the most current version. Data become available through the data portal as they are processed.

## 2013
Domain | Domain Name | Site name | Site ID | Year | Start date | End date
10 | Central Plains | Central Plains Experimental Range | CPER | 2013 | 2017-06-25 | 2017-06-25
10 | Central Plains | North Sterling, CO | STER | 2013 | 2017-06-24 | 2017-06-24
17 | Pacific Southwest | San Joaquin Ecological Range | SJER | 2013 | 2013-06-13 | 2013-06-13
17 | Pacific Southwest | Soaproot Saddle | SOAP | 2013 | 2013-06-12 | 2013-06-15
17 | Pacific Southwest | Lower Teakettle | TEAK | 2013 | 2013-06-14 | 2013-06-15

## 2014
Domain | Domain Name | Site name | Site ID | Year | Start date | End date
1 | Northeast | Harvard Forest | HARV | 2014 | 2014-05-29 | 2014-06-02
1 | Northeast | Bartlett Experimental Forest | BART | 2014 | 2014-06-02 | 2014-06-03
3 | Southeast | Jones Ecological Research Center | JERC | 2014 | 2014-05-21 | 2014-05-21
3 | Southeast | Ordway-Swisher Biological Station | OSBS | 2014 | 2014-05-05 | 2014-05-20
3 | Southeast | Ordway-Swisher Biological Station - Suggs Lake | SUGG | 2014 | 2014-05-05 | 2014-05-20
3 | Southeast | Ordway-Swisher Biological Station -Barco Lake | BARC | 2014 | 2014-05-05 | 2014-05-20
3 | Southeast | Disney Wilderness Preserve | DSNY | 2014 | 2014-05-18 | 2014-05-18

## 2015
Domain | Domain Name | Site name | Site ID | Year | Start date | End date
8 | Ozarks Complex | Talladega National Forest | TALL | 2015 | 2015-07-16 | 2015-07-20
8 | Ozarks Complex | Mayfield Creek | MAYF | 2015 | 2015-07-16 | 2015-07-20
8 | Ozarks Complex | Lenoir Landing | LENO | 2015 | 2015-07-20 | 2015-07-25
8 | Ozarks Complex | Lower Tombigbee River at Choctaw Refuge | TOMB | 2015 | 2015-07-20 | 2015-07-25
8 | Ozarks Complex | Dead Lake | DELA | 2015 | 2015-07-22 | 2015-07-26
8 | Ozarks Complex | Black Warrior River near Dead Lake | BLWA | 2015 | 2015-07-22 | 2015-07-26
7 | Appalachians & Cumberland Plateau | Oak Ridge National Laboratory | ORNL | 2015 | 2015-08-01 | 2015-08-02
7 | Appalachians & Cumberland Plateau | Walker Branch | WALK | 2015 | 2015-08-01 | 2015-08-02
7 | Appalachians & Cumberland Plateau | Great Smoky Mountains National Park | GRSM | 2015 | 2015-08-03 | 2015-08-17
7 | Appalachians & Cumberland Plateau | LeConte Creek | LECO | 2015 | 2015-08-03 | 2015-08-17

## 2016
Domain | Domain Name | Site name | Site ID | Year | Start date | End date
11 | Southern Plains | LBJ Grasslands | CLBJ | 2016 | 2017-04-20 | 2017-04-28
11 | Southern Plains | Pringle Creek | PRIN | 2016 | 2017-04-20 | 2017-04-28
11 | Southern Plains | Klemme Range Research Station | OAES | 2016 | 2017-04-20 | 2017-04-28
11 | Southern Plains | South Pond at KRRS | OAES | 2016 | 2017-04-20 | 2017-04-28
8 | Ozarks Complex | Talladega National Forest | TALL | 2016 | 2017-04-30 | 2017-05-21
8 | Ozarks Complex | Mayfield Creek | MAYF | 2016 | 2017-04-30 | 2017-05-21
8 | Ozarks Complex | Lenoir Landing | LENO | 2016 | 2017-04-30 | 2017-05-21
8 | Ozarks Complex | Lower Tombigbee River at Choctaw Refuge | TOMB | 2016 | 2017-04-30 | 2017-05-21
8 | Ozarks Complex | Dead Lake | DELA | 2016 | 2017-04-30 | 2017-05-21
8 | Ozarks Complex | Black Warrior River near Dead Lake | BLWA | 2016 | 2017-04-30 | 2017-05-21
7 | Appalachians & Cumberland Plateau | Oak Ridge National Laboratory | ORNL | 2016 | 2017-05-30 | 2017-06-24
7 | Appalachians & Cumberland Plateau | Walker Branch | WALK | 2016 | 2017-05-30 | 2017-06-24
7 | Appalachians & Cumberland Plateau | Great Smoky Mountains National Park | GRSM | 2016 | 2017-05-30 | 2017-06-24
7 | Appalachians & Cumberland Plateau | LeConte Creek | LECO | 2016 | 2017-05-30 | 2017-06-24
9 | Northern Plains | Woodworth | WOOD | 2016 | 2017-06-26 | 2017-07-09
9 | Northern Plains | Prairie Pothole | PRPO | 2016 | 2017-06-26 | 2017-07-09
9 | Northern Plains | Dakota Coteau Field School | DCFS | 2016 | 2017-06-26 | 2017-07-09
9 | Northern Plains | Northern Great Plains Research Laboratory | NOGP | 2016 | 2017-06-26 | 2017-07-09
6 | Prairie Peninsula | Konza Prairie Biological Station | KONZ | 2016 | 2017-07-11 | 2017-07-17
6 | Prairie Peninsula | McDiffett Creek | MCDI | 2016 | 2017-07-11 | 2017-07-17
6 | Prairie Peninsula | The University of Kansas Field Station | UKFS | 2016 | 2017-07-11 | 2017-07-17
2 | Mid-Atlantic | Smithsonian Conservation Biology Institute | SCBI | 2016 | 2017-07-19 | 2017-08-09
2 | Mid-Atlantic | Posey Creek | POSE | 2016 | 2017-07-19 | 2017-08-09
2 | Mid-Atlantic | Smithsonian Environmental Research Center | SERC | 2016 | 2017-07-19 | 2017-08-09
2 | Mid-Atlantic | Blandy Experimental Farm | BLAN | 2016 | 2017-07-19 | 2017-08-09
7 | Appalachians & Cumberland Plateau | Mountain Lake Biological Station | MLBS | 2016 | 2017-07-19 | 2017-08-09
1 | Northeast | Lower Hop Brook | HOPB | 2016 | 2017-08-18 | 2017-08-30
1 | Northeast | Harvard Forest | HARV | 2016 | 2017-08-18 | 2017-08-30
1 | Northeast | Bartlett Experimental Forest | BART | 2016 | 2017-08-18 | 2017-08-30
5 | Great Lakes | UNDERC | UNDE | 2016 | 2017-09-01 | 2017-09-14
5 | Great Lakes | Crampton Lake | CRAM | 2016 | 2017-09-01 | 2017-09-14
5 | Great Lakes | Steigerwaldt Land Services | STEI | 2016 | 2017-09-01 | 2017-09-14
5 | Great Lakes | Treehaven | TREE | 2016 | 2017-09-01 | 2017-09-14
5 | Great Lakes | Chequamegon-Nicolet National Forest | CHEQ | 2016 | 2017-09-01 | 2017-09-14 | For related OS data, please search for STEI on the data portal
3 | Southeast | Jones Ecological Research Center | JERC | 2016 | 2017-09-16 | 2017-09-21
3 | Southeast | Ordway-Swisher Biological Station | OSBS | 2016 | 2017-09-23 | 2017-10-03
3 | Southeast | Ordway-Swisher Biological Station - Suggs Lake | SUGG | 2016 | 2017-09-23 | 2017-10-03
3 | Southeast | Ordway-Swisher Biological Station -Barco Lake | BARC | 2016 | 2017-09-23 | 2017-10-03
3 | Southeast | Disney Wilderness Preserve | DSNY | 2016 | 2017-09-23 | 2017-10-03

## 2017
Domain | Domain Name | Field Site | SITE ID | Year | Start date | End date
17 | Pacific Southwest | San Joaquin Ecological Range | SJER | 2017 | 2017-03-21 | 2017-03-25
11 | Southern Plains | LBJ Grasslands | CLBJ | 2017 | 2017-04-28 | 2017-05-09
11 | Southern Plains | Pringle Creek | PRIN | 2017 | 2017-04-28 | 2017-05-09
11 | Southern Plains | Klemme Range Research Station | OAES | 2017 | 2017-04-28 | 2017-05-09
11 | Southern Plains | South Pond at KRRS | OAES | 2017 | 2017-04-28 | 2017-05-09
8 | Ozarks Complex | Talladega National Forest | TALL | 2017 | 2017-05-11 | 2017-05-27
8 | Ozarks Complex | Mayfield Creek | MAYF | 2017 | 2017-05-11 | 2017-05-27
8 | Ozarks Complex | Lenoir Landing | LENO | 2017 | 2017-05-11 | 2017-05-27
8 | Ozarks Complex | Lower Tombigbee River | TOMB | 2017 | 2017-05-11 | 2017-05-27
8 | Ozarks Complex | Dead Lake | DELA | 2017 | 2017-05-11 | 2017-05-27
8 | Ozarks Complex | Black Warrior River near Dead Lake | BLWA | 2017 | 2017-05-11 | 2017-05-27
7 | Appalachians & Cumberland Plateau | Oak Ridge National Laboratory | ORNL | 2017 | 2017-05-29 | 2017-06-04
7 | Appalachians & Cumberland Plateau | Walker Branch | WALK | 2017 | 2017-05-29 | 2017-06-04
6 | Prairie Peninsula | Konza Prairie Biological Station (Agricultural) | KONA | 2017 | 2017-06-06 | 2017-06-14
6 | Prairie Peninsula | Konza Prairie Biological Station | KONZ | 2017 | 2017-06-06 | 2017-06-14
6 | Prairie Peninsula | Kings Creek | KING | 2017 | 2017-06-06 | 2017-06-14
6 | Prairie Peninsula | McDiffett Creek | MCDI | 2017 | 2017-06-06 | 2017-06-14
6 | Prairie Peninsula | The University of Kansas Field Station | UKFS | 2017 | 2017-06-06 | 2017-06-14
9 | Northern Plains | Woodworth | WOOD | 2017 | 2017-06-16 | 2017-06-29
9 | Northern Plains | Prairie Pothole | PRPO | 2017 | 2017-06-16 | 2017-06-29
9 | Northern Plains | Dakota Coteau Field School | DCFS | 2017 | 2017-06-16 | 2017-06-29
9 | Northern Plains | Prairie Lake at Dakota Coteau Field School | PRLA | 2017 | 2017-06-16 | 2017-06-29
9 | Northern Plains | Northern Great Plains Research Facility | NOGP | 2017 | 2017-06-16 | 2017-06-29
12 | Northern Rockies | Yellowstone Northern Range (Frog Rock) | YELL | 2017 | 2017-07-01 | 2017-07-08
12 | Northern Rockies | Blacktail Deer Creek | BLDE | 2017 | 2017-07-01 | 2017-07-08
10 | Central Plains | North Sterling, CO | STER | 2017 | 2017-07-12 | 2017-07-15
2 | Mid-Atlantic | Smithsonian Conservation Biology Institute | SCBI | 2017 | 2017-07-20 | 2017-08-10
2 | Mid-Atlantic | Posey Creek | POSE | 2017 | 2017-07-20 | 2017-08-10
2 | Mid-Atlantic | Smithsonian Environmental Research Center | SERC | 2017 | 2017-07-20 | 2017-08-10
2 | Mid-Atlantic | Blandy Experimental Farm | BLAN | 2017 | 2017-07-20 | 2017-08-10
2 | Mid-Atlantic | Lewis Run | LEWI | 2017 | 2017-07-20 | 2017-08-10
7 | Appalachians & Cumberland Plateau | Mountain Lake Biological Station | MLBS | 2017 | 2017-07-20 | 2017-08-10
1 | Northeast | Harvard Forest | HARV | 2017 | 2017-08-12 | 2017-08-24
1 | Northeast | Lower Hop Brook | HOPB | 2017 | 2017-08-12 | 2017-08-24
1 | Northeast | Bartlett Experimental Forest | BART | 2017 | 2017-08-12 | 2017-08-24
5 | Great Lakes | UNDERC | UNDE | 2017 | 2017-08-26 | 2017-09-08
5 | Great Lakes | Crampton Lake | CRAM | 2017 | 2017-08-26 | 2017-09-08
5 | Great Lakes | Little Rock Lake | LIRO | 2017 | 2017-08-26 | 2017-09-08
5 | Great Lakes | Steigerwaldt Land Services | STEI | 2017 | 2017-08-26 | 2017-09-08
5 | Great Lakes | Treehaven | TREE | 2017 | 2017-08-26 | 2017-09-08
5 | Great Lakes | Chequamegon-Nicolet National Forest | CHEQ | 2017 | 2017-08-26 | 2017-09-08 | For related OS data, please search for STEI on the data portal
3 | Southeast | Jones Ecological Research Center | JERC | 2017 | 2017-09-11 | 2017-09-16
3 | Southeast | Ordway-Swisher Biological Station | OSBS | 2017 | 2017-09-18 | 2017-09-28
3 | Southeast | Ordway-Swisher Biological Station - Suggs Lake | SUGG | 2017 | 2017-09-18 | 2017-09-28
3 | Southeast | Ordway-Swisher Biological Station -Barco Lake | BARC | 2017 | 2017-09-18 | 2017-09-28
3 | Southeast | Disney Wilderness Preserve | DSNY | 2017 | 2017-09-18 | 2017-09-28
7 | Appalachians & Cumberland Plateau | Great Smoky Mountains National Park | GRSM | 2017 | 2017-10-07 | 2017-10-26
7 | Appalachians & Cumberland Plateau | LeConte Creek | LECO | 2017 | 2017-10-07 | 2017-10-26
10 | Central Plains | Central Plains Ecological Range | CPER | 2017 | 2017-05-21 | 2017-05-28
15 | Great Basin | Onaqui-Ault | ONAQ | 2017 | 2017-05-30 | 2017-06-05
15 | Great Basin | Red Butte Creek | REDB | 2017 | 2017-05-30 | 2017-06-05
16 | Pacific Northwest | Wind River Experimental Forest | WREF | 2017 | 2017-06-07 | 2017-06-19
16 | Pacific Northwest | Martha Creek | MART | 2017 | 2017-06-07 | 2017-06-19
16 | Pacific Northwest | Abby Road | ABBY | 2017 | 2017-06-07 | 2017-06-19
17 | Pacific Southwest | Soaproot Saddle | SOAP | 2017 | 2017-06-28 | 2017-07-06
17 | Pacific Southwest | Lower Teakettle | TEAK | 2017 | 2017-06-28 | 2017-07-06
18 | Tundra | Toolik | TOOL | 2017 | 2017-07-12 | 2017-07-28
18 | Tundra | Oksrukuyik Creek | OKSR | 2017 | 2017-07-12 | 2017-07-28
18 | Tundra | Barrow Environmental Observatory | BARR | 2017 | 2017-07-12 | 2017-07-28
19 | Taiga | Caribou Creek at Poker Flats | CARI | 2017 | 2017-07-30 | 2017-08-15
19 | Taiga | Delta Junction | DEJU | 2017 | 2017-07-30 | 2017-08-15
19 | Taiga | Healy | HEAL | 2017 | 2017-07-30 | 2017-08-15
14 | Desert Southwest | Santa Rita Experimental Range | SRER | 2017 | 2017-08-22 | 2017-09-03
14 | Desert Southwest | Jornada LTER | JORN | 2017 | 2017-08-22 | 2017-09-03
13 | Southern Rockies & Colorado Plateau | Niwot Ridge Mountain Research Station | NIWO | 2017 | 2017-09-12 | 2017-09-28
13 | Southern Rockies & Colorado Plateau | Como Creek | COMO | 2017 | 2017-09-12 | 2017-09-28
13 | Southern Rockies & Colorado Plateau | Moab | MOAB | 2017 | 2017-09-12 | 2017-09-28
13 | Southern Rockies & Colorado Plateau | West St. Louis Creek | WLOU | 2017 | 2017-09-12 | 2017-09-28

## 2018
Domain | Domain Name | Field Site | SITE ID | Year | Start date | End date
17 | Pacific Southwest | San Joaquin Ecological Range | SJER | 2018 | 1900-03-31 | 1900-04-04
11 | Southern Plains | LBJ Grasslands | CLBJ | 2018 | 1900-04-17 | 1900-04-25
11 | Southern Plains | Klemme Range Research Station | OAES | 2018 | 1900-04-17 | 1900-04-25
8 | Ozarks Complex | Talladega National Forest | TALL | 2018 | 1900-04-27 | 1900-05-13
8 | Ozarks Complex | Mayfield Creek | MAYF | 2018 | 1900-04-27 | 1900-05-13
8 | Ozarks Complex | Lenoir Landing | LENO | 2018 | 1900-04-27 | 1900-05-13
8 | Ozarks Complex | Lower Tombigbee River | TOMB | 2018 | 1900-04-27 | 1900-05-13
8 | Ozarks Complex | Dead Lake | DELA | 2018 | 1900-04-27 | 1900-05-13
8 | Ozarks Complex | Black Warrior River near Dead Lake | BLWA | 2018 | 1900-04-27 | 1900-05-13
4 | Atlantic Neotropical | Guanica Forest | GUAN | 2018 | 1900-05-08 | 1900-05-24
4 | Atlantic Neotropical | Lajas Experimental Station | LAJA | 2018 | 1900-05-08 | 1900-05-24
7 | Appalachians & Cumberland Plateau | Oak Ridge National Laboratory | ORNL | 2018 | 1900-05-19 | 1900-06-23
7 | Appalachians & Cumberland Plateau | Walker Branch | WALK | 2018 | 1900-05-19 | 1900-06-23
7 | Appalachians & Cumberland Plateau | Great Smoky Mountains National Park | GRSM | 2018 | 1900-05-19 | 1900-06-23
7 | Appalachians & Cumberland Plateau | LeConte Creek | LECO | 2018 | 1900-05-19 | 1900-06-23
7 | Appalachians & Cumberland Plateau | Mountain Lake Biological Station | MLBS | 2018 | 1900-05-19 | 1900-06-23
6 | Prairie Peninsula | Konza Prairie Biological Station (Agricultural) | KONA | 2018 | 1900-05-30 | 1900-06-07
6 | Prairie Peninsula | Konza Prairie Biological Station | KONZ | 2018 | 1900-05-30 | 1900-06-07
6 | Prairie Peninsula | Kings Creek | KING | 2018 | 1900-05-30 | 1900-06-07
6 | Prairie Peninsula | The University of Kansas Field Station | UKFS | 2018 | 1900-05-30 | 1900-06-07
17 | Pacific Southwest | Soaproot Saddle | SOAP | 2018 | 1900-06-16 | 1900-06-26
17 | Pacific Southwest | Lower Teakettle | TEAK | 2018 | 1900-06-16 | 1900-06-26
16 | Pacific Northwest | Wind River Experimental Forest | WREF | 2018 | 1900-07-08 | 1900-07-24
16 | Pacific Northwest | Martha Creek | MART | 2018 | 1900-07-08 | 1900-07-24
16 | Pacific Northwest | Abby Road | ABBY | 2018 | 1900-07-08 | 1900-07-24
18 | Tundra | Toolik | TOOL | 2018 | 1900-07-03 | 1900-07-25
18 | Tundra | Barrow Environmental Observatory | BARR | 2018 | 1900-07-03 | 1900-07-25
12 | Northern Rockies | Yellowstone Northern Range (Frog Rock) | YELL | 2018 | 1900-06-28 | 1900-07-06
12 | Northern Rockies | Blacktail Deer Creek | BLDE | 2018 | 1900-06-28 | 1900-07-06
19 | Taiga | Caribou Creek at Poker Flats | CARI | 2018 | 1900-07-27 | 1900-08-19
19 | Taiga | Delta Junction | DEJU | 2018 | 1900-07-27 | 1900-08-19
19 | Taiga | Healy | HEAL | 2018 | 1900-07-27 | 1900-08-19
14 | Desert Southwest | Santa Rita Experimental Range | SRER | 2018 | 1900-08-18 | 1900-08-30
14 | Desert Southwest | Jornada LTER | JORN | 2018 | 1900-08-18 | 1900-08-30
1 | Northeast | Harvard Forest | HARV | 2018 | 1900-08-30 | 1900-09-12
1 | Northeast | Bartlett Experimental Forest | BART | 2018 | 1900-08-30 | 1900-09-12
3 | Southeast | Jones Ecological Research Center | JERC | 2018 | 1900-09-15 | 1900-10-04
3 | Southeast | Ordway-Swisher Biological Station | OSBS | 2018 | 1900-09-15 | 1900-10-04
3 | Southeast | Ordway-Swisher Biological Station - Suggs Lake | SUGG | 2018 | 1900-09-15 | 1900-10-04
3 | Southeast | Ordway-Swisher Biological Station -Barco Lake | BARC | 2018 | 1900-09-15 | 1900-10-04
3 | Southeast | Disney Wilderness Preserve | DSNY | 2018 | 1900-09-15 | 1900-10-04

## 2019
Domain | Domain Name | Field Site | SITE ID | Year | Scheduled start date | Scheduled end date | Terrestrial (T) Aquatic (A) | Aquatic Site Collocated with Terrestrial Site Flight Box
17 | Pacific Southwest | San Joaquin Ecological Range | SJER | 2019 | 2019-03-25 | 2019-03-28 | T
3 | Southeast | Disney Wilderness Preserve | DSNY | 2019 | 2019-04-03 | 2019-04-23 | T
3 | Southeast | Ordway-Swisher Biological Station | OSBS | 2019 | 2019-04-03 | 2019-04-23 | T
3 | Southeast | Ordway-Swisher Biological Station - Suggs Lake | SUGG | 2019 | 2019-04-03 | 2019-04-23 | A | Y
3 | Southeast | Ordway-Swisher Biological Station -Barco Lake | BARC | 2019 | 2019-04-03 | 2019-04-23 | A | Y
11 | Southern Plains | Klemme Range Research Station | OAES | 2019 | 2019-04-19 | 2019-05-04 | T
11 | Southern Plains | LBJ Grasslands | CLBJ | 2019 | 2019-04-19 | 2019-05-04 | T
11 | Southern Plains | South Pond at KRRS | OAES | 2019 | 2019-04-19 | 2019-05-04 | A | Y
11 | Southern Plains | Blue River | BLUE | 2019 | TBD | TBD | A | N
11 | Southern Plains | Pringle Creek | PRIN | 2019 | TBD | TBD | A | N
8 | Ozarks Complex | Black Warrior River near Dead Lake | BLWA | 2019 | 2019-04-25 | 2019-05-11 | A | Y
8 | Ozarks Complex | Dead Lake | DELA | 2019 | 2019-04-25 | 2019-05-11 | T
8 | Ozarks Complex | Lenoir Landing | LENO | 2019 | 2019-04-25 | 2019-05-11 | T
8 | Ozarks Complex | Lower Tombigbee River | TOMB | 2019 | 2019-04-25 | 2019-05-11 | A | Y
8 | Ozarks Complex | Mayfield Creek | MAYF | 2019 | 2019-04-25 | 2019-05-11 | A | Y
8 | Ozarks Complex | Talladega National Forest | TALL | 2019 | 2019-04-25 | 2019-05-11 | T
15 | Great Basin | Onaqui-Ault | ONAQ | 2019 | 2019-05-06 | 2019-05-13 | T
15 | Great Basin | Red Butte Creek | REDB | 2019 | TBD | TBD | A | N
2 | Mid-Atlantic | Blandy Experimental Farm | BLAN | 2019 | 2019-05-15 | 2019-06-04 | T
2 | Mid-Atlantic | Lewis Run | LEWI | 2019 | 2019-05-15 | 2019-06-04 | A | Y
2 | Mid-Atlantic | Posey Creek | POSE | 2019 | 2019-05-15 | 2019-06-04 | A | Y
2 | Mid-Atlantic | Smithsonian Conservation Biology Institute | SCBI | 2019 | 2019-05-15 | 2019-06-04 | T
2 | Mid-Atlantic | Smithsonian Environmental Research Center | SERC | 2019 | 2019-05-15 | 2019-06-04 | T
6 | Prairie Peninsula | Kings Creek | KING | 2019 | 2019-07-12 | 2019-07-17 | A | Y
6 | Prairie Peninsula | Konza Prairie Biological Station | KONZ | 2019 | 2019-07-12 | 2019-07-17 | T
6 | Prairie Peninsula | Konza Prairie Biological Station (Agricultural) | KONA | 2019 | 2019-05-15 | 2019-05-27 | T
6 | Prairie Peninsula | The University of Kansas Field Station | UKFS | 2019 | 2019-05-15 | 2019-05-27 | T
6 | Prairie Peninsula | McDiffett Creek | MCDI | 2019 | TBD | TBD | A | N
5 | Great Lakes | Chequamegon-Nicolet National Forest | CHEQ | 2019 | 2019-05-29 | 2019-06-23 | T
5 | Great Lakes | Crampton Lake | CRAM | 2019 | 2019-05-29 | 2019-06-23 | A | Y
5 | Great Lakes | Steigerwaldt Land Services | STEI | 2019 | 2019-05-29 | 2019-06-23 | T
5 | Great Lakes | Treehaven | TREE | 2019 | 2019-05-29 | 2019-06-23 | T
5 | Great Lakes | UNDERC | UNDE | 2019 | 2019-05-29 | 2019-06-23 | T
5 | Great Lakes | Little Rock Lake | LIRO | 2019 | TBD | TBD | A | N
17 | Pacific Southwest | Lower Teakettle | TEAK | 2019 | 2019-06-10 | 2019-06-17 | T
17 | Pacific Southwest | Soaproot Saddle | SOAP | 2019 | 2019-06-10 | 2019-06-17 | T
12 | Northern Rockies | Blacktail Deer Creek | BLDE | 2019 | 2019-07-19 | 2019-07-28 | A | Y
12 | Northern Rockies | Yellowstone Northern Range (Frog Rock) | YELL | 2019 | 2019-07-19 | 2019-07-28 | T
18 | Tundra | Barrow Environmental Observatory | BARR | 2019 | 2019-07-02 | 2019-07-26 | T
18 | Tundra | Toolik | TOOL | 2019 | 2019-07-02 | 2019-07-26 | T
18 | Tundra | Oksrukuyik Creek | OKSR | 2019 | TBD | TBD | A | N
16 | Pacific Northwest | Abby Road | ABBY | 2019 | 2019-07-03 | 2019-07-16 | T
16 | Pacific Northwest | Wind River Experimental Forest | WREF | 2019 | 2019-07-03 | 2019-07-16 | T
16 | Pacific Northwest | Martha Creek | MART | 2019 | TBD | TBD | A | N
19 | Taiga | Caribou Creek at Poker Flats | CARI | 2019 | 2019-07-28 | 2019-08-20 | T
19 | Taiga | Delta Junction | DEJU | 2019 | 2019-07-28 | 2019-08-20 | T
19 | Taiga | Healy | HEAL | 2019 | 2019-06-23 | 2019-06-30 | T
9 | Northern Plains | Dakota Coteau Field School | DCFS | 2019 | 2019-07-19 | 2019-08-01 | T
9 | Northern Plains | Northern Great Plains Research Facility | NOGP | 2019 | 2019-07-19 | 2019-08-01 | T
9 | Northern Plains | Prairie Lake at Dakota Coteau Field School | PRLA | 2019 | 2019-07-19 | 2019-08-01 | A | Y
9 | Northern Plains | Prairie Pothole | PRPO | 2019 | 2019-07-19 | 2019-08-01 | A | Y
9 | Northern Plains | Woodworth | WOOD | 2019 | 2019-07-19 | 2019-08-01 | T
13 | Southern Rockies & Colorado Plateau | Como Creek | COMO | 2019 | 2019-08-03 | 2019-08-26 | A | Y
13 | Southern Rockies & Colorado Plateau | Moab | MOAB | 2019 | 2019-08-03 | 2019-08-26 | T
13 | Southern Rockies & Colorado Plateau | Niwot Ridge Mountain Research Station | NIWO | 2019 | 2019-08-03 | 2019-08-26 | T
13 | Southern Rockies & Colorado Plateau | West St. Louis Creek | WLOU | 2019 | TBD | TBD | A | N
14 | Desert Southwest | Jornada LTER | JORN | 2019 | 2019-08-28 | 2019-09-12 | T
14 | Desert Southwest | Santa Rita Experimental Range | SRER | 2019 | 2019-08-28 | 2019-09-12 | T
3 | Southeast | Jones Ecological Research Center | JERC | 2019 | 2019-08-31 | 2019-09-14 | T
1 | Northeast | Harvard Forest | HARV | 2019 | 2019-08-10 | 2019-09-04 | T
1 | Northeast | Bartlett Experimental Forest | BART | 2019 | 2019-08-10 | 2019-09-04 | T
1 | Northeast | Hop Brook | HOPB | 2019 | TBD | TBD | A | N

## 2020
Domain | Domain Name | Field Site | Site ID | Year | Scheduled start date | Scheduled end date | Terrestrial (T) Aquatic (A)
01 | Northeast | Harvard Forest | HARV | 2020 | 2020-08-08 | 2020-09-12 | T
01 | Northeast | Bartlet Experimental Forest | BART | 2020 | 2020-08-08 | 2020-09-12 | T
01 | Northeast | Hop Brook | HOPB | 2020 | 2020-08-08 | 2020-09-12 | A
02 | Mid-Atlantic | Blandy Experimental Farm | BLAN | 2020 | 2020-07-24 | 2020-08-14 | T
02 | Mid-Atlantic | Smithsonian Conservation Biology Institute | SCBI | 2020 | 2020-07-24 | 2020-08-14 | T
02 | Mid-Atlantic | Smithsonian Environmental Research Center | SERC | 2020 | 2020-07-24 | 2020-08-14 | T
02 | Mid-Atlantic | Lewis Run | LEWI | 2020 | 2020-07-24 | 2020-08-14 | A
02 | Mid-Atlantic | Posey Creek | POSE | 2020 | 2020-07-24 | 2020-08-14 | A
05 | Great Lakes | Chequamegon-Nicolet National Forest | CHEQ | 2020 | 2020-07-01 | 2020-07-22 | T
05 | Great Lakes | Steigerwaldt Land Services | STEI | 2020 | 2020-07-01 | 2020-07-22 | T
05 | Great Lakes | Treehaven | TREE | 2020 | 2020-07-01 | 2020-07-22 | T
05 | Great Lakes | UNDERC | UNDE | 2020 | 2020-07-01 | 2020-07-22 | T
05 | Great Lakes | Crampton Lake | CRAM | 2020 | 2020-07-01 | 2020-07-22 | A
05 | Great Lakes | Little Rock Lake | LIRO | 2020 | 2020-07-01 | 2020-07-22 | A
09 | Northern Plains | Northern Great Plains Research Facility | NOGP | 2020 | 2020-06-13 | 2020-07-02 | T
09 | Northern Plains | Woodworth | WOOD | 2020 | 2020-06-13 | 2020-07-02 | T
09 | Northern Plains | Dakota Coteau Field School | DCFS | 2020 | 2020-06-13 | 2020-07-02 | T
09 | Northern Plains | Prairie Lake at Dakota Coteau Field School | PRLA | 2020 | 2020-06-13 | 2020-07-02 | A
09 | Northern Plains | Prairie Pothole | PRPO | 2020 | 2020-06-13 | 2020-07-02 | A
10 | Great Plains | Central Plains Ecological Range | CPER | 2020 | 2020-06-12 | 2020-06-15 | T
10 | Great Plains | North Sterling, CO | STER | 2020 | 2020-06-12 | 2020-06-29 | T
10 | Great Plains | Arikaree River | ARIK | 2020 | 2020-06-12 | 2020-06-29 | A
12 | Northern Rockies | Yellowstone Northern Range (Frog Rock) | YELL | 2020 | 2020-07-04 | 2020-07-16 | T
12 | Northern Rockies | Blacktail Deer Creek | BLDE | 2020 | 2020-07-04 | 2020-07-16 | A
13 | Southern Rockies | Rocky Mountain National Park | RMNP | 2020 | 2020-06-16 | 2020-06-29 | T
14 | Desert Southwest | Santa Rita Experimental Range | SRER | 2020 | 2020-08-22 | 2020-09-07 | T
14 | Desert Southwest | Sycamore Creek | SYCA | 2020 | 2020-08-22 | 2020-09-07 | A
14 | Desert Southwest | Jornada LTER | JORN | 2020 | 2020-09-08 | 2020-09-12 | T
16 | Pacific Northwest | Wind River Experimental Forest | WREF | 2020 | 2020-07-20 | 2020-08-02 | T
16 | Pacific Northwest | Abby Road | ABBY | 2020 | 2020-07-20 | 2020-08-02 | T
16 | Pacific Northwest | Martha Creek | MART | 2020 | 2020-07-20 | 2020-08-02 | A